## RTM
Requirement ID | Module | Requirement Description | Test Case(s) | Bug ID(s) | Status | Fix Priority
REQ-SORT-01 | Products / Sorting | Sort dropdown must reorder products for every account type | C23 | KAN-4 | Defect(s) logged | High
REQ-SORT-02 | Products / Sorting | Selected sort order must persist across navigation | C24 | KAN-5 | Defect(s) logged | Low
REQ-PROD-01 | Products | Each product must display its own correct image | C27 | KAN-6 | Defect(s) logged | Medium
REQ-PROD-02 | Products / Cart | Every product must be addable to the cart for every account type | C52 | KAN-7 | Defect(s) logged | High
REQ-PROD-03 | Products | Clicking a product must open that exact product's detail page | C52 | KAN-8 | Defect(s) logged | High
REQ-PROD-04 | Products | Every product detail page must load valid product data | C52 | KAN-9 | Defect(s) logged | High
REQ-CART-01 | Cart | Cart contents must be scoped to the account that added them | C30 | KAN-10 | Defect(s) logged | Medium
REQ-CART-02 | Cart | Cart badge count must reflect only items actually present in the cart | C52 | KAN-11 | Defect(s) logged | Medium
REQ-NAV-01 | Navigation | Product detail page navigation should be context-aware (UX, not a hard requirement) | C25 | KAN-12 | UX suggestion logged | Medium
REQ-CHK-01 | Checkout | Checkout must be blocked entirely when the cart is empty | C33 | KAN-13, KAN-14 | Defect(s) logged | High / Medium
REQ-CART-03 | Cart | Cart item quantity must be adjustable, or clearly fixed by design | — (no case yet) | KAN-15 | Defect logged (no test case yet) | Medium
REQ-CHK-02 | Checkout | Checkout must complete successfully for every account type | C40 | KAN-16 | Defect(s) logged | High
REQ-CHK-03 | Checkout | Shipping fields must apply reasonable input-length limits | C47 | KAN-17 | Defect(s) logged | Low
REQ-AUTH-01 | Auth | Valid credentials must log the user in successfully | C1 | — | No defects logged | —
REQ-AUTH-02 | Auth | Invalid credentials must be rejected with a clear error | C2, C16, C3, C4, C17 | — | No defects logged | —
REQ-AUTH-03 | Auth | Locked-out accounts must be blocked with a specific error | C5 | — | No defects logged | —
REQ-AUTH-04 | Auth | Logout must fully end the session (no back-button access) | C20 | — | No defects logged | —
REQ-CART-04 | Cart | Add/remove actions must keep the cart badge accurate | C10, C11, C12, C35 | — | No defects logged | —
REQ-CHK-04 | Checkout | Required checkout fields must block submission when empty | C37 | — | No defects logged | —
REQ-CHK-05 | Checkout | Order summary must match cart contents exactly | C15, C43 | — | No defects logged | —